## Project
id | depends_of | start_date | source | internal_owner | external_owner | task | days | forecast | accomplished | pct_progress
0 |  | 2023-03-27 | SOURCE1 | Marcus Smith | Marcus Smith | Task 01 | 0 | 2023-03-27 | 2023-03-30 | 100
1 | 0 | 2023-03-30 | SOURCE1 | Jhon Doe | Simone Evans | Task 02 | 3 | 2023-04-04 | 2023-04-04 | 80
2 | 1 | 2023-04-04 | SOURCE1 | Jhon Doe | Kalvin Rogers | Task 03 | 3 | 2023-04-10 | 2023-04-10 | 0
3 | 2 | 2023-04-10 | SOURCE1 | Jhon Doe | William Anderson | Task 04 | 1 | 2023-04-11 | 2023-04-11 | 0
4 | 3 | 2023-04-11 | SOURCE1 | Jhon Doe | Erika Quiñones | Task 05 | 2 | 2023-04-13 | 2023-04-13 | 0
5 | 4 | 2023-04-13 | SOURCE1 | Jhon Doe | Fábio Popper | Task 06 | 4 | 2023-04-19 | 2023-04-19 | 0
6 | 1 | 2023-04-04 | SOURCE1 | Marcus Smith | Juan Eduardo Fernández | Task 07 | 2 | 2023-04-06 | 2023-04-06 | 0
7 | 5 | 2023-04-19 | SOURCE1 | Jhon Doe | Waldison Kramer | Task 08 | 5 | 2023-04-27 | 2023-04-27 | 0
8 | 7 | 2023-04-27 | SOURCE1 | Jhon Doe | Simone Carminatti | Task 09 | 0 | 2023-04-27 | 2023-04-27 | 0
9 | 8 | 2023-04-27 | SOURCE1 | Jhon Doe | Simone Carminatti | Task 10 | 20 | 2023-05-26 | 2023-05-26 | 0
10 | 9 | 2023-05-26 | SOURCE1 | Jhon Doe | Leonardo Santos | Task 11 | 10 | 2023-06-12 | 2023-06-12 | 0
11 | 10 | 2023-06-12 | SOURCE1 | Jhon Doe | Marisa Heidegger | Task 12 | 10 | 2023-06-26 | 2023-06-26 | 0
12 | 9 | 2023-05-26 | SOURCE1 | Jhon Doe | Tools Team | Task 13 | 15 | 2023-06-19 | 2023-06-19 | 0
13 | 8;11 | 2023-06-26 | SOURCE1 | Jhon Doe | Marisa Heidegger | Task 14 | 10 | 2023-07-10 | 2023-07-10 | 0
14 |  | 2023-04-06 | SOURCE2 | Jhon Doe | Marisa Heidegger | Task 15 | 6 | 2023-04-17 | 2023-04-17 | 70
15 | 14 | 2023-04-17 | SOURCE2 | Jhon Doe | Regerio Moraes | Task 16 | 2 | 2023-04-19 | 2023-04-19 | 0
16 | 15 | 2023-04-19 | SOURCE2 | Jhon Doe | Regerio Moraes | Task 17 | 5 | 2023-04-27 | 2023-04-27 | 0
17 | 14 | 2023-04-06 | SOURCE2 | Jhon Doe | Regerio Moraes | Task 18 | 2 | 2023-04-11 | 2023-04-11 | 20
18 |  | 2023-04-10 | SOURCE3 | Jhon Doe | Cassiano dos Santos | Task 19 | 0 | 2023-04-10 | 2023-04-10 | 0
19 | 18 | 2023-04-10 | SOURCE3 | Jhon Doe | Simone Evans | Task 20 | 5 | 2023-04-17 | 2023-04-17 | 0
20 | 18 | 2023-04-10 | SOURCE3 | Marcus Smith | Juan Eduardo Fernández | Task 21 | 2 | 2023-04-12 | 2023-04-12 | 0
21 | 19 | 2023-04-17 | SOURCE3 | Jhon Doe | Cassiano dos Santos | Task 22 | 4 | 2023-04-24 | 2023-04-24 | 0
22 | 19 | 2023-04-24 | SOURCE3 | Jhon Doe | Regerio Moraes | Task 23 | 2 | 2023-04-26 | 2023-04-26 | 0
23 |  | 2023-03-31 | SOURCE4 | Jhon Doe | Simone Carminatti | Task 24 | 6 | 2023-04-11 | 2023-04-11 | 70
24 |  | 2023-03-31 | SOURCE4 | Vivian Grey | Lucia Cappello | Task 25 | 3 | 2023-04-05 | 2023-04-04 | 100
25 |  | 2023-03-31 | SOURCE5 | Marcus Smith | Ismael Ferraz | Task 26 | 5 | 2023-04-10 | 2023-04-10 | 60
26 |  | 2023-04-05 | SOURCE6 | Vivian Grey | Marisa Heidegger | Task 27 | 2 | 2023-04-10 | 2023-04-10 | 80
27 | 26 | 2023-04-10 | SOURCE6 | Vivian Grey | Marisa Heidegger | Task 28 | 3 | 2023-04-13 | 2023-04-13 | 0
28 | 27 | 2023-04-13 | SOURCE6 | Vivian Grey | Marisa Heidegger | Task 29 | 5 | 2023-04-20 | 2023-04-20 | 0
29 |  | 2023-04-03 | SOURCE7 | Jhon Doe | Simone Evans | Task 30 | 4 | 2023-04-10 | 2023-04-10 | 70
30 | 29 | 2023-04-10 | SOURCE7 | Jhon Doe | Origin Source | Task 31 | 5 | 2023-04-17 | 2023-04-17 | 0
31 | 30 | 2023-04-17 | SOURCE7 | Jhon Doe | Origin Source | Task 32 | 2 | 2023-04-19 | 2023-04-19 | 0
32 | 29 | 2023-04-10 | SOURCE7 | Marcus Smith | Juan Eduardo Fernández | Task 33 | 5 | 2023-04-17 | 2023-04-17 | 0
33 | 29;44 | 2023-05-24 | SOURCE7 | Jhon Doe | Infra Source | Task 34 | 10 | 2023-06-07 | 2023-06-07 | 0
34 | 33 | 2023-06-07 | SOURCE7 | Jhon Doe | Regerio Moraes | Task 35 | 10 | 2023-06-22 | 2023-06-22 | 0
35 | 34 | 2023-06-22 | SOURCE7 | Jhon Doe | Regerio Moraes | Task 36 | 3 | 2023-06-27 | 2023-06-27 | 0
36 | 35 | 2023-06-27 | SOURCE7 | Jhon Doe | Jhon Doe | Task 37 | 1 | 2023-06-28 | 2023-06-28 | 20
37 | 36 | 2023-06-28 | SOURCE7 | Jhon Doe | Marisa Heidegger | Task 38 | 10 | 2023-07-12 | 2023-07-12 | 0
38 | 37 | 2023-07-12 | SOURCE7 | Jhon Doe | Marisa Heidegger | Task 39 | 5 | 2023-07-19 | 2023-07-19 | 0
39 | 38 | 2023-07-19 | SOURCE7 | Jhon Doe | Kalvin Rogers | Task 40 | 5 | 2023-07-26 | 2023-07-26 | 0
40 | 39 | 2023-07-26 | SOURCE7 | Jhon Doe | Marisa Heidegger | Task 41 | 5 | 2023-08-02 | 2023-08-02 | 0
41 | 31;32 | 2023-04-19 | SOURCE7 | Jhon Doe | Erika Quiñones | Task 42 | 3 | 2023-04-25 | 2023-04-25 | 0
42 | 41 | 2023-04-25 | SOURCE7 | Jhon Doe | Fábio Popper | Task 43 | 5 | 2023-05-03 | 2023-05-03 | 0
43 | 42 | 2023-05-03 | SOURCE7 | Jhon Doe | Waldison Kramer | Task 44 | 5 | 2023-05-10 | 2023-05-10 | 0
44 | 43 | 2023-05-10 | SOURCE7 | Jhon Doe | Infra Source | Task 45 | 10 | 2023-05-24 | 2023-05-24 | 0
Formulas:
forecast = WORKDAY([start_date],[days],holidays)
accomplished = [forecast]
start_date = [forecast, row above]
start_date = [accomplished, row above]

## Holidays
Day | Description
2023-04-07 | Easter [BR]
2023-04-21 | Tiradentes [BR]
2023-05-01 | Worker Day [BR]
2023-06-08 | Corpus Christi [BR]
2023-09-07 | Brazil Independence Day [BR]
2023-10-12 | Nossa Senhora Aparecida [BR]
2023-11-02 | Finados [BR]
2023-11-15 | Proclamação da República [BR]
2023-12-24 | Christmas Eve [BR]
2023-12-25 | Christmas [BR]