## Project
id | depends_of | start_date | source | internal_owner | external_owner | task | days | forecast | accomplished | pct_progress
0 |  | 2023-03-31 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Liberação ISLON 250 | 6 | 2023-04-11 | 2023-04-11 | 100
1 | 0; | 2023-04-11 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Instalação CONTROL M | 3 | 2023-04-14 | 2023-04-14 | 40
2 |  | 2023-04-06 | HYBRIS | Chelida Arantes | Otto Melo | Solicitação de Ciência PCP | 2 | 2023-04-11 | 2023-04-14 | 90
3 |  | 2023-04-10 | PRISMA | Pablo Veinberg | Edivaldo Batista | Kickoff implementação infra | 0 | 2023-04-10 | 2023-04-10 | 20
4 | 3; | 2023-04-10 | PRISMA | Pablo Veinberg | Edivaldo Batista | Cronograma de entrega | 3 | 2023-04-13 | 2023-04-13 | 0
5 |  | 2023-04-05 | OAM | Pablo Veinberg | Flavia Conti | Implantação CHG0041724 | 7 | 2023-04-17 | 2023-04-17 | 60
6 |  | 2023-04-06 | IDM | Wellington Oliveira | Daniel Kawamoto | Homologação 3ra Rodada | 3 | 2023-04-12 | 2023-04-12 | 100
7 |  | 2023-04-05 | VIVOCORP MOVEL | Pablo Veinberg | Flavio Silva | Implantação CHG0038215 | 2 | 2023-04-10 | 2023-04-10 | 90
8 | 7; | 2023-04-10 | VIVOCORP MOVEL | Pablo Veinberg | José Edson | Homologação | 4 | 2023-04-14 | 2023-04-14 | 0
9 | 5; | 2023-04-17 | OAM | Pablo Veinberg | Daniel Kawamoto | Homologação | 3 | 2023-04-20 | 2023-04-20 | 0
10 | 0; | 2023-04-11 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Scan de vulnerabilidade REQ000008002389 | 4 | 2023-04-17 | 2023-04-17 | 30
11 | 1; | 2023-04-14 | HYBRIS | Pablo Veinberg | André Bueno | Desenvolvimento Extração | 7 | 2023-04-26 | 2023-04-26 | 0
12 | 11;19 | 2023-04-27 | HYBRIS | Pablo Veinberg | Flavio Silva | Desenvolvimento Ingestão | 7 | 2023-05-09 | 2023-05-09 | 0
13 | 9; | 2023-04-20 | OAM | Pablo Veinberg | Flavia Conti | Pós produção | 5 | 2023-04-28 | 2023-04-28 | 0
14 |  | 2023-04-05 | SAP COMISSIONS | Pablo Veinberg | Elizete Augusto | DAS | 2 | 2023-04-10 | 2023-04-10 | 90
15 | 14; | 2023-04-10 | SAP COMISSIONS | Wellington Oliveira | Wellington Oliveira | Análise de segurança | 3 | 2023-04-13 | 2023-04-13 | 0
16 | 14; | 2023-04-10 | SAP COMISSIONS | Pablo Veinberg | Cassiano | QI Origem | 4 | 2023-04-14 | 2023-04-14 | 0
17 | 16; | 2023-04-14 | SAP COMISSIONS | Pablo Veinberg | Flavio Silva | QI Destino | 2 | 2023-04-18 | 2023-04-18 | 0
18 | 1; | 2023-04-14 | HYBRIS | Pablo Veinberg | Pablo Veinberg | AFT ACCOUNT | 5 | 2023-04-24 | 2023-04-24 | 0
19 | 18; | 2023-04-24 | HYBRIS | Pablo Veinberg | Flavio Silva | Script de transferência | 3 | 2023-04-27 | 2023-04-27 | 0
20 | 2;0 | 2023-04-14 | HYBRIS | Pablo Veinberg | André Bueno | Validação Hybris | 10 | 2023-05-02 | 2023-05-02 | 0
21 | 20; | 2023-05-02 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Controles Operacionais [INFRA] | 5 | 2023-05-09 | 2023-05-09 | 0
22 | 21; | 2023-05-09 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Monitoração [INFRA] | 5 | 2023-05-16 | 2023-05-16 | 0
23 | 22; | 2023-05-16 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Gerar CRQ Passagem Produção [INFRA] | 1 | 2023-05-17 | 2023-05-17 | 0
24 | 23; | 2023-05-17 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Executar CRQ Passagem Produção [INFRA] | 5 | 2023-05-24 | 2023-05-24 | 0
25 | 24; | 2023-05-24 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Acompanhamento Pós Produção [INFRA] | 20 | 2023-06-22 | 2023-06-22 | 0
26 | 25; | 2023-06-22 | HYBRIS | Pablo Veinberg | Edivaldo Batista | Concluir JIRA [INFRA] | 1 | 2023-06-23 | 2023-06-23 | 0
27 | 12; | 2023-05-09 | HYBRIS | Pablo Veinberg | Flavia Conti | Documentação para CHG | 10 | 2023-05-23 | 2023-05-23 | 0
28 | 27;24 | 2023-06-22 | HYBRIS | Pablo Veinberg | Flavio Silva | Tramitação CHG | 5 | 2023-06-29 | 2023-06-29 | 0
29 | 28; | 2023-06-29 | HYBRIS | Pablo Veinberg | Flavia Conti | Pós produção | 5 | 2023-07-06 | 2023-07-06 | 0
30 | 6; | 2023-04-12 | IDM | Pablo Veinberg | Diego Deboni | Correção de inconsistências e subida em produção | 3 | 2023-04-17 | 2023-04-17 | 30
31 | 30; | 2023-04-17 | IDM | Pablo Veinberg | Flavio Silva | Ajustes na ingestão | 3 | 2023-04-20 | 2023-04-20 | 0
32 | 6; | 2023-04-12 | IDM | Pablo Veinberg | Flavio Silva | Verificar caracteres especiais e corrigir na ingestão | 1 | 2023-04-13 | 2023-04-13 | 0
33 | 6; | 2023-04-12 | IDM | Pablo Veinberg | Flavio Silva | Exclusão da tabela 12c_ent_assing | 2 | 2023-04-14 | 2023-04-14 | 0
Formulas:
forecast = WORKDAY([start_date],[days],holidays)
accomplished = [forecast]
start_date = [accomplished, row above]

## Holidays
Day | Description
2023-04-07 | Easter [BR]
2023-04-21 | Tiradentes [BR]
2023-05-01 | Worker Day [BR]
2023-06-08 | Corpus Christi [BR]
2023-09-07 | Brazil Independence Day [BR]
2023-10-12 | Nossa Senhora Aparecida [BR]
2023-11-02 | Finados [BR]
2023-11-15 | Proclamação da República [BR]
2023-12-24 | Christmas Eve [BR]
2023-12-25 | Christmas [BR]